## Sheet1
| Sprint One | [7 empty] | Sprint Two
| Sprint One Tasks | [7 empty] | Sprint Two Tasks
Task | Start Hours | Week One | Week Two | Week Three | Week Four |  | Total Hours | Task | Start Hours | Week One | Week Two | Week Three | Week Four |  | Total Hours
Task 1 | 2 | 2 | 0 | 0 | 0 |  | 2 | Task 1: Find dynamic HTML solution to work cross platform | 2 | 1 | 0 | 0 | 0 |  | 1
Task 2 | 4 | 1 | 0 | 0 | 3 |  | 4 | Task 2: Modify for current use | 2 | 2 | 0 | 0 | 0 |  | 2
Task 3 | 2 | 1 | 0 | 0 | 1 |  | 2 | Task 3: Implement HTML solution | 2 | 2 | 0 | 0 | 0 |  | 2
Task 4 | 1 | 1 | 0 | 0 | 0 |  | 1 | Task 4: Test on all browsers | 2 | 2 | 0 | 0 | 0 |  | 2
Task 5 | 5 | 0 | 0 | 0 | 1 |  | 1 | Task 5: Create login sequence (simple & Google) | 3 | 1 | 1 | 0 | 0 |  | 2
Task 6 | 2 | 0 | 0 | 0 | 0 |  | 0 | Task 6: Store user login information | 2 | 0 | 0 | 0 | 0 |  | 0
Task 7 | 1 | 0 | 0 | 0 | 0 |  | 0 | Task 7: Utilise personal information on website | 3 | 0 | 1 | 0 | 0 |  | 1
Task 8 | 3 | 0 | 0 | 0 | 1 |  | 1 | Task 8: Implement security for user information | 3 | 0 | 1 | 0 | 0 |  | 1
Task 9 | 1 | 0 | 0 | 0 | 0 |  | 0 | Task 9: Find plugin for media streaming | 2 | 2 | 0 | 0 | 0 |  | 2
Task 10 | 5 | 0 | 0 | 0 | 2 |  | 2 | Task 10: Adapt web player for our use | 2 | 2 | 0 | 0 | 0 |  | 2
Task 11 | 5 | 0 | 0 | 0 | 2 |  | 2 | Task 11: Preview setup for several file types | 2 | 1 | 0 | 0 | 0 |  | 1
Task 12 | 2 | 0 | 0 | 0 | 1 |  | 1 | Task 12: Create custom preview window | 2 | 1 | 0 | 0 | 0 |  | 1
Task 13 | 5 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0
Task 14 | 3 | 0 | 0 | 0 | 1 |  | 1 | [7 empty] | 0
Task 15 | 3 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0
| Total Times |  |  |  |  | Total Hours | 17 |  | Total Times |  |  |  |  | Total Hours | 17
Actual Remaining Hours | 44 | 39 | 39 | 39 | 27 |  | 27 | Actual Remaining Hours | 54 | 40 | 37 | 37 | 37 |  | 37
Estimated Remaining Hours | 44 | 35.2 | 26.4 | 17.6 | 8.8 |  | 0 | Estimated Remaining Hours | 27 | 21.6 | 16.2 | 10.8 | 5.4 |  | 0
Sprint One Catchup
[8 empty] | Task | Start Hours | Week One | Week Two | Week Three | Week Four |  | Total Hours
[8 empty] | Task 1 | 0 | 0 | 0 | 0 | 0 |  | 0
[8 empty] | Task 2 | 0 | 0 | 0 | 0 | 0 |  | 0
[8 empty] | Task 3 | 0 | 0 | 0 | 0 | 0 |  | 0
[8 empty] | Task 4 | 0 | 0 | 0 | 0 | 0 |  | 0
[8 empty] | Task 5 | 4 | 0 | 0 | 0 | 0 |  | 0
[8 empty] | Task 6 | 2 | 0 | 0 | 0 | 0 |  | 0
[8 empty] | Task 7 | 1 | 0 | 0 | 0 | 0 |  | 0
[8 empty] | Task 8 | 2 | 0 | 0 | 0 | 0 |  | 0
[8 empty] | Task 9 | 1 | 0 | 0 | 0 | 0 |  | 0
[8 empty] | Task 10 | 3 | 0 | 0 | 0 | 0 |  | 0
[8 empty] | Task 11 | 3 | 0 | 0 | 0 | 0 |  | 0
[8 empty] | Task 12 | 1 | 0 | 0 | 0 | 0 |  | 0
[8 empty] | Task 13 | 5 | 0 | 0 | 0 | 0 |  | 0
[8 empty] | Task 14 | 2 | 0 | 0 | 0 | 0 |  | 0
[8 empty] | Task 15 | 3 | 0 | 0 | 0 | 0 |  | 0